PROFESSIONAL SERVICES CONTRACT

This Contract (hereinafter referred to as the "CONTRACT") is made between:

IOS Partners, Inc. (hereinafter referred to as "IOS"), having offices at 311 Mendoza Avenue, Coral Gables, FL, USA 33134:

And

Alex Jeffries, (hereinafter referred to as “CONSULTANT”), residing at [please insert address].

- The CONSULTANT shall provide the consulting services described in Appendix I: Scope of Work and in respect of Appendix II: The Terms of Reference to “Developing the Blue Tourism Cluster for the Indian Ocean”.

- The specific Scope of Work for the CONSULTANT is provided in Appendix I.

- The CONSULTANT shall perform all work in accordance with sound professional or other governing practices, subject to the satisfaction and acceptance by IOS and Cap Business Océan Indien (CBOI) and Agence Française de Développement (AFD), hereinafter referred to individually and collectively as “CLIENT”.

Invoicing of fees

- This CONTRACT sets a maximum lump sum amount for fees of US$10,000.00 (Ten Thousand US Dollars and 00/100), excluding travel expenses.

- CONSULTANT will invoice IOS for the professional services rendered in pursuit of the accomplishment of his duties and responsibilities, the delivery and acceptance of the deliverables described in Appendix I: Scope of Work by IOS and the CLIENT.

Payment will be made according to the following schedule:

| DELIVERABLE | AMOUNT |
| --- | --- |
| - Ten percent (10%) of the lump sum amount shall be paid within 20 days from the CLIENT’s approval of the Launching Report and receipt of CONSULTANT´s invoice. | US$1,000.00 (One thousand US Dollars and 00/100) |
| - Ten percent (10%) of the lump sum amount shall be paid within 20 days from the CLIENT’s approval of the Literature Review Report and receipt of CONSULTANT´s invoice. | US$1,000.00 (One thousand US Dollars and 00/100) |
| - Twenty percent (20%) of the lump sum amount shall be paid within 20 days from the CLIENT’s approval of the Blue Tourism Cluster Development Blueprint, including Regional Framework and Three-Year Action Plan and receipt of CONSULTANT´s invoice. | US$2,000.00 (Two thousand US Dollars and 00/100) |
| - Twenty-five percent (25%) of the lump sum amount shall be paid within 20 days from the CLIENT’s approval of the Capacity Building Plan, Monitoring & Evaluation Framework and Regional Governance and Collaborative Platform and receipt of CONSULTANT´s invoice. | US$2,500.00 (Two thousand Five-hundred US Dollars and 00/100) |
| - Thirty-five percent (35%) of the lump sum amount shall be paid within 20 days from the CLIENT’s approval of the Financing Strategy, Blue Investment Pipeline and Indian Ocean Blue Tourism Brand and receipt of CONSULTANT´s invoice. | US$3,500.00 (Three thousand Five-hundred US Dollars and 00/100) |

IOS shall not be required to pay any invoice for fees sent more than 30 days after completion of work or any invoice for expenses sent more than 30 days after these expenses have been incurred.

- IOS will make no deductions for any taxes from CONSULTANT’s invoices nor will it have an obligation or liability to pay or reimburse any taxes related to CONSULTANT’s income.

- Payment to CONSULTANT shall be made in the form of electronic bank transfer to the designated bank account or by corporate check. IOS will wire the total amount owed to the CONSULTANT with originating bank fees for its own account, however, IOS is not responsible for any fees that are deducted from the payment by the CONSULTANT’s recipient bank over which it has no control.

Authority and management

- CONSULTANT shall not have authority to act for and shall not make any commitments on behalf of IOS, except in relation to decisions relative to the management of the PROJECT, which will be made in consultation with and agreement from IOS.

- CONSULTANT shall not discuss contractual arrangements with other experts on this Project or the CLIENT and such shall remain confidential during the course of undertaking the Services and shall survive the term of this CONTRACT.

- CONSULTANT agrees to indemnify IOS for any losses or damages sustained by IOS as a direct or indirect result of CONSULTANT’s actions to commit IOS except in relation to decisions relative to the management of the PROJECT, which were made in consultation with and agreement from IOS.

- Additionally, CONSULTANT agrees to indemnify IOS for all losses or damages resulting directly or indirectly from any acts or omissions, which constitute negligence in the performance of the tasks listed in the CONTRACT.

CONSULTANT’s conduct and confidentiality of documents

- CONSULTANT shall conform to all laws, regulations, and local customs governing CONSULTANT conduct in the place of assignment. If CONSULTANT violates any such law or customs, CONSULTANT alone shall be responsible for all fines, penalties or other costs resulting from such violation.

- CONSULTANT shall not improperly disclose any of the trade secrets, proprietary information or confidential information of IOS.  If CONSULTANT does improperly disclose such information, CONSULTANT shall be liable to IOS for all costs and damages which result either directly or indirectly from the wrongful/inappropriate disclosure.

- It is understood by CONSULTANT that confidential information includes but is not limited to reports, documents, correspondence, draft publications, maps, drawings, notes, specifications, statistics, work product in any form, and technical data, computer programs and computer related information system designs or models and procedures sent to IOS and/or the CLIENT as part of the services under this CONTRACT and remain IOS’ and CLIENT’s sole property. This obligation shall survive the term of this CONTRACT.

- All documents that CONSULTANT prepares, or confidential information or documents that might be given to them in the course of this Project shall be considered the exclusive property of the CLIENT. Under no circumstances shall any such information or documents be utilized or commercialized without CLIENT or IOS’ written consent.

- While performing its duties for the CONTRACT, CONSULTANT will defend IOS’ interests.

Termination of the contract

- IOS may terminate the CONTRACT without prior notice in the following cases:

  - If CONSULTANT does not perform all of the duties required, as defined in Appendix I;

  - If CONSULTANT is in breach of any of the terms and conditions of the CONTRACT; and

  - If the PROJECT is terminated by the CLIENT.

- CONSULTANT may terminate this CONTRACT without prior notice if any of the following shall occur:

- IOS breaches any of the terms and conditions of the CONTRACT;

- IOS unreasonably withholds any approvals requested by CONSULTANT;

- IOS refuses to provide any resources CONSULTANT reasonably requests.

- In the event of termination of the CONTRACT by IOS, IOS shall pay CONSULTANT for all work submitted and approved by IOS and the CLIENT up to the date of such termination, and IOS will be responsible to return CONSULTANT to his place of residence, if CONSULTANT is in the field at the time such termination is made.

Project Related Expenses

- The CONSULTANT shall be reimbursed for all justifiable project related expenses approved by IOS in advance and based on actual costs, including visas, local transportation and other miscellaneous travel expenses. Reimbursement of all expenses will be made further to the presentation of a duly completed expense report as found in Appendix III, attached hereto, to be submitted by the CONSULTANT upon return from a mission. IOS will not accept any submission of expense claims unless it is completed using IOS’ Expense Report Form/Guidelines in Appendix III and is supported by original receipts and documentation. CONSULTANT shall seek prior approval of IOS for incurring any project related expenses. Payment to CONSULTANT shall be made in full within thirty calendar days from approval of the expenses by IOS Financial Management. Expense Reports must be submitted for approval within 30 days following the completion of mission. IOS shall not be required to pay any invoice for expenses sent more than 30 days after these expenses have been incurred.

- Transportation to and from Madagascar will be the responsibility of IOS. IOS will either buy an economy class return tickets directly or will reimburse the CONSULTANT the cost of an economy class return ticket to and from Madagascar upon submission of relevant original boarding passes, invoice and ticket stubs. The CONSULTANT shall seek prior approval of IOS for purchase of his ticket to and from Madagascar, if ticket is to be purchased directly by the CONSULTANT.

- When traveling, IOS will pay for accomodation directly, or will reimburse the CONSULTANT for the actual cost of accommodation, up to maximum daily rate of US$80.00 in Madagascar. In addition, the CONSULTANT will be provided an allowance (per diem) of US$65.00 in Madagascar, per day for meals and incidental expenses applicable to the travel and the actual number of days worked in the CLIENT country unless these expenses have been directly paid by IOS during the mission. The allowance shall be apportioned as follows:

Breakfast 15%

Lunch 25%

Dinner  40%

Incidentals 20%

All client meals shall be fully reimbursed and the per diem shall be adjusted according to the percentage allotted for that meal. If CONSULTANT is provided with accommodation that includes breakfast, the percentage of their per diem which is allotted for breakfast (15%), shall be deducted each day in which CONSULTANT utilizes said accommodations.

- CONSULTANT may receive an expense advance, upon request and submission of an invoice prior to departure on a mission. This expense advance will cover 50% of the estimated expenses for the mission to be incurred by the CONSULTANT relative to that specific mission prior to its commencement.

- CONSULTANT will receive no Company fringe benefits (or any other benefits not expressly set forth herein) during the term of this CONTRACT, except for travel medical insurance and medical evacutions during field missions. CONSULTANT shall be responsible for obtaining insurance coverage (including but not limited to workers’ compensation, life, accident, etc.), which he finds necessary, or desirable, solely at CONSULTANT’s own expense.

General Conditions

- This Contract shall be governed by and construed in accordance with the laws of the State of Florida, U.S.A.

- Any dispute or disagreement which cannot be resolved by the parties and any controversy, claim or dispute otherwise arising out of or in connection with this CONTRACT, or the breach thereof, shall be settled by arbitration under the rules of the American Arbitration Association. An arbitration award shall be a condition precedent to any litigation proceedings hereunder. Arbitration proceedings shall be held in the Metropolitan Miami, Florida area or such other place as is mutually acceptable to both parties. The award in any arbitration proceeding shall  be  final  and  binding  upon  both  parties  and  judgment thereon may be entered in any court of competent jurisdiction upon  application of either of the parties.

- This CONTRACT (together with its Appendices) represents and constitutes the entire agreement between the parties and shall not be explained, modified, or contradicted by any prior or contemporaneous negotiations, representations or agreements, either written or oral. This CONTRACT may be amended only by a written instrument signed by each party.

This CONTRACT shall become effective once it is signed by both parties and end on or before February 28, 2027.

IN WITNESS WHEREOF, the parties have caused this CONTRACT to be signed as follows:

IOS Partners, Inc.

Signature: ______________

Name: Tea Alania

Title: COO and VP for Project Management and Development

Dated:

Telephone: +1 (305) 648-2877

Fax: +1 (305) 446-7122

CONSULTANT

Signature: ______________

Name:	Alex Jeffries

Expertise: Branding and Communications Specialist

Dated:

Telephone:

Email:	alex.jeffries@gmail.com

Country of Citizenship: USA

Country of Origin: USA

Bank details:

Address:

Account name:

Account #:

Bank Transit #:

Institution #:

SWIFT#:

Appendix I

SCOPE OF WORK FOR ALEX JEFFRIES

BRANDING & COMMUNICATION SPECIALIST

Minimum Standards for Contractual Compliance

Acceptance of contractual compliance by CLIENT and IOS: CONSULTANT fully understands that any and all material, statement of completion, documents, and/or reports are considered as DRAFT documents by the CLIENT until IOS Project Management has been officially informed by CLIENT of acceptance and contractual compliance with defined performance indicators.

Standardization of Report Submission: IOS Project Management will provide sample formats to be used for all report submission(s).  These report formats will be formulated to meet the defined standards and requisites of the CLIENT and will be considered as the only format acceptable for report submission.  IOS Project Management accepts that the format maybe subject to further enhancement as a result of the expressed requirements of the CLIENT.

Notification of Final Acceptance of Drafts: IOS Project Management reserves the right to require changes, enhancements and/or any other improvements to the draft submission by CONSULTANT in order to ensure compliance with the requirements of the CLIENT.  In all instances, no deliverable will be considered completed until IOS Project Management, in written form, informs CONSULTANT of its final acceptance.

List of Deliverables and Reporting Requirements: The CONSULTANT shall be responsible for addressing any comments and suggestions provided by IOS further to preliminary review of the deliverables submitted by the CONSULTANT.  Any such feedback shall be satisfactorily addressed by the CONSULTANT directly and/or in coordination with IOS’ other experts, as needed, prior to submission of any such deliverables to the CLIENT.

Project Background

Cap Business Océan Indien (CBOI) – which is the brand image of the Union of the Chambers of Commerce and Industry of the Indian Ocean, an association regrouping six (6) constitutive territories, namely Comoros, Madagascar, Mauritius, Mayotte, Reunion and Seychelles – has secured funding from the French Development Agency (AFD) for ‘Developing the Blue Tourism Cluster for the Indian Ocean’, a project aimed at promoting blue tourism, biodiversity regeneration, economic development, and regional collaboration in line with the Action Plan for Sustainable Tourism in these six island territories of the Indian Ocean.

This technical assistance is structured around four (4) components – blue tourism, biodiversity regeneration, economic development, and regional collaboration – and six (6) specific objectives (SO); namely:

SO1: Literature Review Report

SO2: Blue Tourism Cluster Development Plan

SO3: Stakeholder Engagement

SO4: Capacity building

SO5: Financing strategy

SO6: Indian Ocean Blue Tourism Brand

To accomplish these objectives, the PROJECT is expected to produce to the following outputs:

- A Blue Tourism Blueprint with a concrete and actionable timeline over the next three years;

- The establishment of an online technical platform to facilitate knowledge sharing and collaboration with the private stakeholders; and

- Capacity building programs to strengthen skills, practices, and institutional frameworks.

SCOPE OF WORK

During the duration of this CONTRACT, Mr. Alex Jeffries will serve the role of Branding & Communication Specialist.

CONSULTANT will be tasked with providing technical guidance and advice to the IOS’ team and the CLIENT in relation to the implementation of the PROJECT, and will ensure the timely and coordinated preparation and submission of high-quality inputs to PROJECT deliverables, reports and presentations, while guaranteeing quality assurance and control prior to submission to IOS and the CLIENT.

Under the guidance of the IOS’ Project Management Team and Technical Team Leader, CONSULTANT will have the following general responsibilities:

- Lead the development of the Indian Ocean Blue Tourism brand identity, integrating sustainability, culture, innovation, and regional connectivity.

- Develop messaging, promotional materials, and stakeholder engagement tools to support brand adoption and visibility.

- Coordinate with regional stakeholders to ensure brand alignment and consistent communication.

- Contribute to the desing of a capacity building plan for SMEs to support the adoption of sustainable tourism practices.

- Contribute to the facilitation of participatory stakeholder workshops, consultations, and technical committee meetings at national and regional levels.

- Participare in the preparation of the list of required documentation and stakeholder meetings to be submitted to the CLIENT.

- Participate in IOS’ Project Management meetings, discussions with other experts, the CLIENT and other relevant stakeholders.

Technical Activities and Outputs

The CONSULTANT will be involved in Phases 0, 1, 3, 4 and 6 of the PROJECT, to provide technical advice on destination branding and sustainable tourism marketing. More specifically, the CONSULTANT will participate in the following activities:

PHASE 0 – Initial Mobilization

- Project Launching

CONSULTANT shall participate in the Project Launching activities and ensure early collaboration and engagement with the rest of the IOS’ technical team and PROJECT stakeholders.

This includes the kick-off meeting, initial mobilization and tasks assignments; alignment of  project goals and objectives; refinement of the methodological approach and implementation schedule; stakeholder mapping; and definition of communication and reporting protocols with CLIENT and rest of stakeholders.

Particular attention will be paid during this phase to clarifying the sequencing of tasks, and ensuring that branding and communication activities are not initiated before sufficient alignment is achieved on cluster definition, product development, and market positioning.

Phase 0 output: Launching Report – including the kick-off meeting and initial mobilization; confirmation of project goals and objectives; methodological approach and implementation schedule, communication and reporting mechanisms, etc.

PHASE 1 — Diagnostic and baseline analysis

- Literature Review

CONSULTANT shall support the rest of the IOS’ technical team to collect and analyze data, as needed.

This Literature Review shall include:

- Identification of priority market segments;

- Analysis of market expectations regarding sustainability and blue tourism;

- Definition of a clear value proposition for the Blue Tourism Cluster;

- Alignment between:

  - Product development (clusters)

  - Target markets

  - Branding and communication strategy

CONSULTANT shall ensure that the identification of priority market segments and value propositions considers the regional dimension of the cluster, with a view to avoiding duplication of similar tourism products across the six destinations and promoting complementarity based on each territory’s specific assets.

Phase 1 output: Literature Review Report – including a review of industrial and technical reports, policy document, best practice; and the identification of the data gaps, research, and policies that need to be addressed through the PROJECT.

PHASE 3 — Regional Governance and Collaborative Platform

- Stakeholder Engagement

CONSULTANT shall provide technical input to and assist the Stakeholder Engagement and Facilitation Specialist, and rest of IOS’ technical team, for the development of the Regional Governance and Collaborative Platform.

The aim of this activity is to establish a collaborative platform and mobilize stakeholder participation in technical committees, validation workshops, and regional consultations to provide them with the opportunity to share their expertise and perspectives for achieving the outcomes of the blue tourism cluster. The goal is to strengthen ownership and alignment from coastal and island communities directly impacted by tourism and marine activities.

The process will aim to guide stakeholders toward coordinated regional positioning, avoiding fragmented or competing approaches between destinations, particularly where similar tourism concepts are being developed.

This shall include the following:

- Developing of an online platform or adapt to an existing one for the technical committee.

- Assisting CBOI in addressing technical issues raised during preliminary discussions and consultations; and

- Undertaking a stakeholders' workshop for the validation of the three-year Action Plan and Blueprint for the Blue Tourism Cluster Development Plan.

Phase 3 output: Stakeholder Engagement – including the establishment of a technical committee per island of the key stakeholders; the development of an online platform for the technical committee; and the undertaking of a stakeholders’ validation workshop.

PHASE 4 — Capacity Building and Monitoring & Evaluation

- Capacity Building

CONSULTANT shall contribute to the development of a Capacity Building Plan by providing practical guidance on destination branding, market positioning, product differentiation, and alignment with target segments, with particular attention to avoiding the replication of similar tourism products across destinations. CONSULTANT shall also assist in the identification of training needs, target groups and feasible delivery modalities, as well as in the delivery trainings to stakeholders in the Indian Ocean region.

CONSULTANT shall also participate in ‘The MOVE - Blue Tourism’ and collaborate with Cap Business OI and the rest of the IOS’ technical team to provide relevant input and logistical support, as needed.

The objective is to achieve the capacity building program in line with Blue Tourism Cluster Development Plan and the Action Plan for Sustainable Tourism, targeted at all six island territories. The aim is to provide technical support and accompany existing enterprises, especially SMEs and community-based operators in the tourism and blue economy sector with the necessary skills and knowledge to develop, implement, and market new tourism products and services which have the potential to transform their activities as per the requirements for sustainability integration of the blueprint.

The technical support strategy for small enterprises of the tourism and blue economy sectors shall focus on destination branding and sustainable tourism marketing. The key sub-activities shall include the following:

  - Survey exercise to assess existing capacity, knowledge and skill gaps, and resource requirements.

  - Development of a capacity-building program to accompany the entreprises with technical expertise and skills in destination branding and sustainable tourism marketing that can be integrated along their activities.

  - Capacity building workshops, and webinars with at least 50 entreprises, relevant stakeholders and agencies involved in vocational and academic trainings.

  - Desig  of an evaluation tool to monitor and record the enterprise progress and provide technical assistance to ensure effective implementation of sustainable tourism practices.

Phase 4 output: Capacity Building – including the undertaking of a regional capacity needs assessment linked to the stakeholders' mapping; the design of a training program; the development of a monitoring and evaluation tool; the delivery of capacity building workshops in all the six territories (hybrid); and the participation in the ‘The MOVE - Blue Tourism’ event – a regional in-person workshop, with a minimum of 50 stakeholders from the private sector, to enable them to share, co-create, promote and give visibility to the Indian Ocean Blue Tourism Initiatives.

PHASE 6 — Digital Branding, Certification, and Communication

- Indian Ocean Blue Tourism Brand

CONSULTANT shall lead the development of the Indian Ocean Blue Tourism brand identity.

The objective is to develop a market-driven regional brand for Blue Tourism in the Indian Ocean ensuring a coherent and cohesive approach to positioning the region as a sustainable and high-value tourism destination on the global market.

This phase will be implemented once priority clusters have been identified and their market positioning clarified, in order to ensure that the brand reflects concrete, market-ready tourism experiences

Rather than being conceived as a purely visual and promotional exercise, the brand will be grounded in actual tourism experiences and priority clusters, reflecting both existing and emerging products across the six island territories. It will serve as a strategic tool for market access, differentiation and value creation, supporting operators in reaching targeted international markets and aligning with evolving demand for sustainability.

The CONSULTANT will lead the development of a regional brand, including:

- A clear value proposition for Blue Tourism in the Indian Ocean;

- Identification of target audiences and priority market segments;

- A positioning statement aligned with market expectations;

- A set of key narratives, including sustainability, biodiversity, community engagement, and innovation .

The brand will be designed to:

- Reflect actual experiences available or under development within selected clusters;

- Be adaptable across the six island contexts, while maintaining a coherent regional identity; and

- Support cluster-based differentiation, allowing each territory to highlight its specific assets rather than applying uniform messaging

In this perspective, the brand will contribute to enhancing the international visibility of the region, strengthening its positioning in the global sustainable tourism market, and reinforcing market access for tourism and blue economy operators.

In parallel, the brand will be linked to a pragmatic and official eco-certification framework, for tourism enterprises, products, and services (as per the recommendations of the blueprint), aligned with internationally recognisez standards such as the Global Sustainable Tourism Council (GSTC), but adapted to the specific environmental and socio-economic realities of the six island territories. The objective is to ensure that certification acts as a market-enabling mechanism, supporting credibility and differentiation rather than creating unnecessary barriers for operators.

This shall include the following activities:

  - Development of the brand concept, including value proposition, positioning, narratives, and visual identity (logo note and brand attributes);

  - Validation of the proposed brand and visual identity with the relevant stakeholders through the regional stakeholders’ platform.

  - Technical support to CBOI for the development of a market oriented communication and promotion strategy aligned with priority segments and distribution channels (including tour operators, digital platforms and online travel agencies), emphasizing added value of the blue tourism cluster, its sustainability credentials, and its contribution to regional development and ocean conservation.

  - Support the articulation between the regional brand and the shared cluster positioning, ensuring that the cluster is implemented as a coordinated regional offering across the six destinations. This includes guiding stakeholders to develop complementary, rather than competing, experiences by differentiating target markets, value propositions, and narratives based on each territory’s specific assets and comparative advantages.

  - Assistance to CBOI’s communication team in the positioning of the brand based with the supporting narratives on all six islands under a common vision of regenerative marine tourism, community empowerment, and ocean resilience.

  - Assistance to CBOI’s communication team in developing targeted content and tools (digital and offline) to strengthen the visibility and attractiveness of the brand among priority audiences (tourists, impact investors, and sustainability-oriented entreprises).

  - Contribution to the development of an eco-certification framework with clear certification criteria, operational procedures, and implementation guidelines aligned with the brand promise.

  - Support awareness-raising and stakeholder engagement around the certification system, including pathways toward recognition by relevant authorities and partners

  - Identification of practical incentives and synergies (e.g. marketing advantages, access to financing, investment incentives) to encourage the adoption of the brand and certification by enterprises.

Phase 6 output: Indian Ocean Blue Tourism Brand – including brand concept, logo note and attributes; communication material for the CLIENT’s communication team; eco-certification framework and guidelines including list of local schemes such as tax relief, investment incentives, financing criteria and marketing advantages for certified enterprises; and the formal presentation of the Blueprint to authorities, and regional and international partners.

DELIVERABLES

The CONSULTANT shall work together with the rest of the IOS’ team to prepare and complete assigned PROJECT deliverables in a timely manner; including the presentation of each final deliverable to the CLIENT, as outlined in the table below.

CONSULTANT will be responsible for quality assurance and quality control prior to submission of his inputs to IOS and the CLIENT.

Both, English and French shall be used for the preparation of main deliverables, key meetings and workshops, capacity-building activities, and the dissemination of results.

| PHASE | KEY ACTIVITIES | OUTPUT | FORMAT | SUBMISSION TIMELINE |
| --- | --- | --- | --- | --- |
| DELIVERABLE #1 |  |  |  |  |
| Phase 0: Launching Report | a. Kick-off meeting and initial mobilization; confirmation of project goals and objectives; methodological approach and implementation schedule, communication and reporting mechanisms, etc. | a. Refined methodology and workplan. | PPT, PDF, PowerPoint | 2-3 weeks from project commencement |
| DELIVERABLE #2 |  |  |  |  |
| Phase 1: Literature Review Report | a. Review of industrial and technical reports, policy document, best practices b. Identification of the data gaps, research, and policies that need to be addressed through the project. | a. Literature Review Report (with gaps & recommendations) | PDF, Word, PowerPoint | Month 1 |
| DELIVERABLE #3 |  |  |  |  |
| Phase 3: Stakeholder Engagement | a. Establish a technical committee per island of the key stakeholders. | a. Technical committee established. | PDF, Word, PowerPoint | Month 2 – 5 |
|  | b. Develop an online platform for the technical committee. | b. Online platform established. | NA | Month 2 - 5 |
|  | c. Validation of the three-year Action Plan and Blueprint for the Blue Tourism Cluster Development Plan | c. Stakeholders' engagement workshop with at least 50 stakeholders. | PDF, Word, PowerPoint | Month 2 - 5 |
| DELIVERABLE #4 |  |  |  |  |
| Phase 4: Capacity Building | a. Conduct a regional capacity needs assessment linked to the stakeholders' mapping. | a. Skills gap survey report. | PDF, Word, PowerPoint | Month 4 - 6 |
|  | b. Design a training strategy with clear ToR for the technical assistance to be provided. | b. Technical support strategy. | PDF, Word | Month 4 - 6 |
|  | c. Co-organisation with Cap Business IO of the ‘The Move- Blue Tourism’ event, the regional workshop, with a minimum of 50 stakeholders from the private sector of the region and enabling them to share, co-create, promote and give visibility to the Indian Ocean Blue Tourism Initiatives. | c. One (1) regional capacity building event: The MOVE. | NA | Month 4 - 6 |
|  | d. Conduct capacity building programmes. | d. Capacity building workshops conducted in all the six territories (hybrid/online). | NA | Month 4 - 6 |
|  | e. Create a monitoring and evaluation tool. | e. Monitoring and evaluation toolkit. | PDF, Word, PowerPoint | Month 4 - 6 |
| DELIVERABLE #5 |  |  |  |  |
| Phase 6: Indian Ocean Blue Tourism Brand | a. Brand concept, logo note and attributes. | a. Brand concept note, logo note and identity. | PDF, Word, PowerPoint | Month 6 - 8 |
|  | b. Communication material for Cap Business OI's communication team. | b. Communication and promotion strategy; digital content package. | PDF, Word, PowerPoint | Month 6 - 8 |
|  | c. Eco-certification framework and guidelines including list of local schemes such as tax relief, investment incentives, financing criteria and marketing advantages for certified enterprises. | c. Eco-certification framework (brand package, manual, guidelines and toolkit). | PDF, Word, PowerPoint | Month 6 - 8 |
|  | d. Submission of final Blueprint, brand concept note, logo note and identity and eco-certification framework. | d. Validation workshop with technical committee. | PDF, Word, PowerPoint | Month 7 - 8 |
|  | e. Presentation of the Blueprint and formal recognition with authorities, regional and international partners. | e. Launching of logo event and presentation of Blueprint and eco-certification framework. | NA | Month 8 |

Note: The CONSULTANT will follow the proposed methodology, enclosed as a separate attachment to this CONTRACT, which is subject to change subsequent to agreements reached with the CLIENT during the Initial Mobilization phase and thereafter, if any.

MEETINGS

CONSULTANT is expected to travel to attend The MOVE event. During travel, the CONSULTANT shall use low-cost, eco-friendly accommodation where possible, in accordance with sustainability principles of the blue tourism industry.

The rest of stakeholders’ workshops; CLIENT, and internal progress review meetings, shall be organized on an as-needed basis and conducted via teleconference.

Appendix II

PROJECT TERMS OF REFERENCE FOR DEVELOPING THE BLUE TOURISM CLUSTER FOR THE INDIAN OCEAN

Enclosed as a separate attachment to this CONTRACT.

Appendix III

EXPENSE REPORT

General

This document lays out the expense policies of IOS Partners, Inc. Travel is an important component of the operations of IOS Partners, Inc, and it is important that these policies advance our goals of controlling costs while still ensuring the staff’s well-being.  The policies enumerated here apply to all expenses conducted under the auspices of the IOS Partners, Inc, whether by employee or independent contractor and whether or not billable to a client.

The appropriate manager or partner and the project administrator (for project related expenses) have the responsibility to ensure that adequate documentation and/or justification is provided by the employee in order to obtain reimbursement of expenses.  The Expense Report should be computer generated or, if prepared manually, completed in black or blue ink, without erasures or "white-out".  After your signature and approval by both the manager or partner and the project administrator (for project related expenses), the report should be forwarded to the Coral Gables, Florida.

Expense Reports must be submitted for approval within 30 days following the completion of mission.  Once submitted to the Coral Gables Accounting section, all payments shall be made in full within fifteen calendar days from approval of the expenses by IOS Financial Management.  Partial payment will be made for items in dispute or those that require clarification.

Meals and incidentals expenses (M&IE) – Meals and incidental expenses, including all personal telephone calls, tips, personal transportation to meals, laundry expenses etc. will be covered by payment of the flat M&IE portion of the per diem rate.  The M&IE portion of the per diem is based on the rate in effect for the city in which the night was spent. If meals are included within the price of the lodging, the M&IE allowance will be reduced by the associated amount for the particular meal included:  breakfast, 15 percent; lunch, 25 percent; and dinner, 40 percent.

Business meals – When traveling on IOS Partners, Inc. it may sometimes be necessary to host a business lunch or dinner for clients.   All such expenditures require practice managing director approval.  It is important that the business meal be clearly identified as such and that the date, location, purpose, and attendees are listed.  However, if a traveler attends or hosts an IOS Partners, Inc. funded business meal while receiving per diem he/she must deduct the associated amount for the particular meal from the per diem claimed for the day of the meal:  breakfast, 15 percent; lunch, 25 percent; and dinner, 40 percent.

Miscellaneous expenses – Reasonable miscellaneous expenses associated with travel such as costs of visas, passports, exit fees, currency exchange fees, business communications, and local transportation costs for business purposes are reimbursable travel expenses.

Receipts - documentary evidence of payment must be submitted for the following items in order to obtain reimbursement.

    - Airline Transportation (boarding passes, used flight coupons, copy of itinerary)

    - Automobile rentals

    - Hotel accommodations (detailed, itemized receipts required)

    - Telephone and fax expenses for business purposes ONLY (detailed, itemized receipts required)

    - Railroad and bus transportation

    - Taxi services (if available)

    - International money exchange receipts showing exchange rates or copies of FX

    - All parking lot charges

    - Gasoline for rental cars

    - Any unusual items that need to be pre-approved

Payment Instructions – Accounting maintains files of mailing addresses and wiring instructions for all employees and independent contractors.  It is corporate policy to pay consultants by check.  Please inform these instructions in writing using the form IOS Banking Instructions.  Payment by wire transfer will made on an exceptional basis and should be presented to management for approval.  If and when approved the form IOS Wire Transfer Instructions should be filled out.

Reimbursement of Expenses

Please submit a request for reimbursement of expenses within 30 days of returning from your trip.  All payments will be processed and paid during the 30 days after receiving complete documentation. Partial payment will be done for items in dispute or those that require receipts or clarification.

PROCEDURES FOR FILLING OUT FORM

Travel expenses will only be reimbursed after submission of a travel expense form that includes all appropriate approval signatures and appropriate receipts in the required format. IOS Partners, Inc. Accounting staff have been instructed not to reimburse expenses not meeting these requirements.

- Expenses should be submitted on the standard travel expense form.

- Original expense receipts must be submitted.  Failure to provide original receipts will result in rejection of expense invoices (an IOS Partners, Inc. policy). Please note that receipts are not required for meals.

- Receipts must be taped down to blank, 8 1/2" x 11" paper in chronological order.  Do NOT staple receipts.  They need to be taped down to facilitate photocopying and recording of expenses.  The REC# number indicates the support invoice document that will be used to justify the expense.  This number must be sequential and unique by expense. This will facilitate the process of identifying a receipt/invoice with the   expense report sheet. Receipts in other language than English MUST contain a note describing the type of expense (business meals, hotel, taxi, telephone, internet etc.). Please note that receipts are not required for meals.

- Receipts in a foreign currency MUST have the exchange rate and the U.S. dollar amount noted on the receipt.  Please attach to separate pages all foreign exchange conversion receipts for the period as backup for figures being submitted.  If conversion rates are not provided, the IOS Partners, Inc. Accounting Department will derive rates from its rate conversion program or the Wall Street Journal.  These rates may not be as favorable as ones actually received by the traveler.

- The DATE column must be filled out for each expense.

- The PER DIEM/MEAL column must be filled out with the maximum per diem rate that was defined in the contract. The OVERHEAD EXPENSES/MEAL column must be filled out ONLY when an extraordinary business meal has occurred.

- The PER DIEM/LODGING column must be filled out with the real lodging expense supported by a receipt. The maximum amount to be reimbursed is defined in the contract.

- Expenses on the hotel bill other than accommodation costs, for which the consultant requests reimbursement, must be identified and explained.  Note that expenses of a personal nature (alcoholic beverages; personal services such as barber and beautician; personal phone calls; and special room services such as in-room movies, in-room bars or extra-cost facilities such as health clubs) are not reimbursable.

- Receipts should be obtained for all business-related taxi and other transportation expenses.  If receipts are not available, consultants should list the date, location and cost of all transactions on a blank sheet of 8 1/2" x 11" paper.

- Business telephone calls may be reimbursed IF the business purpose of the call is noted on either a log or the hotel receipt, along with the name of the person called, the date and an explanation of the business nature of the call.

- MISCELLANEOUS expenses must be entered on the second page of the expense report. Receipts and explanations for "Miscellaneous" business related expenses must be attached.  In addition to business telephone calls, these may include photocopying, purchase of supplies or materials and other travel incidentals.  Descriptions are also required for expenses included on hotel bills.

UNALLOWABLE EXPENSES:

- Alcoholic beverages, personal services (e.g., barber, beautician), in-room movies, mini-bars, health facilities are not reimbursable.

- The difference between the per diem maximums and the actual costs if not billable to the client, are not allowable overhead costs; these costs may only be reimbursed with the applicable managing director approval.

- IOS Partners, Inc. will only allow travel under coach airfares unless special agreement has been reached prior to travel.

Implementation

If there are issues or questions of interpretation regarding these policies, contact Anne Dekker at (305) 648-2877 or by e-mail at adekker@iospartners.com.

Please access the Expense Report format by clicking on the following icon:

Submission timelines are indicative and subject to changes throughout the course of project implementation.